## Mobile Expenses Estimation
Mobile Expenses
Sno | Sequence | Activities | Development | Testing | Description | Status | Exception Handling | Migrating to Production Environment(Live)
1 | HRMS Sequence | Login | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Getting the Expense Details For Each Employee Code. | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Insert into Expesnes Details For Each employee Code | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Insert into logger table the status of the each bills. | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
2 | Voucher Creation | Login | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Enter the Each Employee details on the Basic Input Screen | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Enter the Each Employee expenses Into Credit Debit Screen | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Create Voucher for Each Employee. | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
3 | Voucher Authorization | Login | 4Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Enter the Details on the Basic Input Screen. | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Check if the Voucher is Authorized or Processed for Each Employee | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs
|  | Move the Authorized to Pending bank settlement or HRMS Update Pending | 4 Hrs | 3 Hrs | NA | Open | 1 Hr | 2 Hrs

## Travel Expenses Estimation
Travel Expenses
Sno | Sequence | Activities | Development | Testing(UAT) | Description | Status | Exception Handling | Migrating to Production Environment(Live)
1 | HRMS Sequence | Login | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Getting the Expense Details For Each Employee Code. | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Insert into Expesnes Details For Each employee Code | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Insert into logger table the status of the each bills. | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
2 | Voucher Creation | Login | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Enter the Each Employee details on the Basic Input Screen | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Enter the Each Employee expenses Into Credit Debit Screen | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Create Voucher for Each Employee. | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
3 | Voucher Authorization | Login | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Enter the Details on the Basic Input Screen. | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Check if the Voucher is Authorized or Processed for Each Employee | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs
|  | Move the Authorized to Pending bank settlement or HRMS Update Pending | 6 Hrs | 5 Hrs | NA | Open | 2 Hrs | 2 Hrs